## Slide 1: Roadmap: 4 steps done, 2 in review, 4 days to freeze
RAG assistant on French green & innovation business aids · status as of Sat 17 Oct 2026
Done
In progress
Blocked
Not started
13–14 Oct
0
Scoping
14 Oct
1
Data foundations
15 Oct
2
Pieces + keyword search
16 Oct
3
Exam machine, 40 questions
16 Oct
4
Search by meaning
16–17 Oct
5
Ranking + reranker
17 Oct
6
Answer generation
18 Oct
7
Agent + tracking
19 Oct
8
Final evaluation
19 Oct
9
Bonuses + UI
20 Oct
10
Code freeze v1.0
21 Oct
11
Defence
TODAY
PR #8 in review
PR #8 in review
Done since 14 Oct
Aids cut into 865 searchable pieces, checked by hand
Keyword search + 40-question exam machine (run_eval.py)
bge-m3 chosen; 2 rerankers tested; free ×3 fix adopted
Next, in order
Review and merge PR #8 (search + ranking)
Pick the answering model (Ollama) and write answers with sources
Add agent tools, then score everything on held-out
To decide today
Who owns which step from Sat to Tue (slide 15)
Rule: one approval before every merge
Who records the backup demo video
Source: repo and GitHub, 17 Oct 2026. Dates are targets; owners per step to be agreed at the meeting.
Notes: Steps 0 to 3 are done and merged. Step 4 (search by meaning) is built and measured; its PR #8 waits for review. Step 5 (reranker) has its code ready; its benchmark runs next. Everything from step 6 on is still ahead, with 4 days left before the Tuesday 23:59 freeze.

## Slide 2: Phase 1 recap (14 Oct): a verified foundation
Steps 0–1 of the roadmap, as presented on 14 Oct
504
aids selected from 2,442
20 → 40
test questions (40 today)
17 → 35
automated checks passing (35 today)
1
error in the government data found and fixed
1
Chose the use case
A funding finder for SMEs with a green or innovation project; scope and git rules agreed
2
Selected 504 aids
2,442 → 504 with three checkable rules: enough text, no duplicates, green or innovation
3
Confirmed the source
data.gouv.fr “Aides entreprises”, Licence Ouverte; all 504 aids match today's official file
4
Enriched every aid
Region, deadline, company size, aid type and funder added; a region error in the source fixed
5
Wrote 20 test questions
Facts, eligibility, regions, deadlines, plus trick questions and hacking attempts
6
Built a safety net
Automated checks, an identical rebuild with one command, and a full data card
Known limits: 47% of local aids have no region on file · 15 dead source links. Phase 2 starts on the next slides.
Notes: Phase 1 delivered the data foundation: a rule-based, reproducible 504-aid corpus, a confirmed source and licence, and a fixed region error in the government data. The figures in green show then and now.

## Slide 3: How the 9 files fit together: one record per aid
aides.csv points to lookup tables by ID; we join 5 of them into every aid
Joined
Partly joined
Not used
natures.csv · 12 rows
Aid type: grant, loan, tax relief… · 503 of 504 aids
projets.csv · 101 rows
Project themes, used for the green + innovation filter · 504 of 504
profils.csv · 17 rows
Eligible business profiles (industry, crafts, retail…) · 504 of 504
financeurs.csv · 1,427 rows
Funder names, and postcodes used to infer some regions · 504 of 504
territoires.csv · 39,348 rows
Area → region, fixed with an official region table · 228 of 432 local aids
contacts.csv · 7,925 rows
Contact IDs kept, details not joined yet · 503 of 504
aides.csv
2,442 aids, filtered to 504
aids.jsonl
504 clean records, labels instead of IDs
Not used
domaines.csv domain names already written in aides.csv
niveaux.csv national / regional / EU level already in aides.csv
Joins are made on IDs (e.g. aides.natures → natures.id_typ). Counts from data/processed/aids.jsonl, 14 Oct 2026. No external dataset was merged.
Notes: The raw dataset is relational: aides.csv stores IDs that point to lookup tables. The selection script resolves them into readable labels and writes one self-contained record per aid.

## Slide 4: Phase 2: from clean data to measurable search
15–16 Oct · steps 2 to 5 · every choice below is backed by a score on our 40 test questions
Notes: Phase 2 turns the clean corpus into a search engine. The rule from the brief: no component counts as working until it is scored on held-out questions, with speed and cost tracked.

## Slide 5: The whole system in one picture
What happens to a question, left to right. Colour = status today.
Done
In progress
Not started
Question
in French, from an SME
Keyword search
BM25, French words. Good at names: “CIR”, “Bpifrance”
2
Meaning search
bge-m3 fingerprints. Good at paraphrases
4
Merge (RRF)
Rank-based fusion of both lists
4
Reranker
Re-reads question + piece; keeps top 5
5
Answer (LLM)
Answer with aid IDs, or “I don't know”
6
Agent tools
Filter region, date, type; fetch an aid
7
Underneath: 865 pieces 504 aids cut into searchable pieces, each with an ID-card header (step 2)
Around it: the exam machine run_eval.py asks all 40 questions and logs answer, sources, tokens, latency, tool calls (step 3)
Numbers in circles = roadmap step. The brief requires: hybrid search (BM25 + dense) + reranking, citations, structured outputs, tracking, evaluation.
Notes: Each question goes through two search engines in parallel: keyword search for exact names, meaning search for paraphrases. Their two ranked lists are merged with Reciprocal Rank Fusion. A reranker then reads each candidate together with the question and keeps the best five. The answering model will write the answer from those five pieces only, citing the aid IDs. The exam machine measures every stage.

## Slide 6: Step 2 · Cutting the 504 aids into 865 searchable pieces
Each piece carries an ID-card header, so even a lone “amount” piece knows which aid it belongs to
1 aid
Objet
Dépenses éligibles
Conditions
Montant
Bénéficiaires
Header: name · type · region · funder · deadline
Objet + dépenses éligibles…
Header: name · type · region · funder · deadline
Montant + bénéficiaires… (15% overlap)
865
pieces from 504 aids
281
aids fit in one piece
300–700
tokens per piece (target 300–800)
Chart: Right aid in top 5, keyword search
| Without header | With header
Dev (17 questions) | 76.5 | 100
Held-out (16 questions) | 75 | 87.5
Decision: keep the header on every piece (+23 points on dev). Placeholders %pme% and %mini% are replaced by their real meaning.
Source: eval/retrieval_bm25.json (BM25 variants). Long aids are split by section, never mid-word; a piece repeats ~15% of the previous one.
Notes: One aid becomes one piece when it is short enough; long aids are split by section. Each piece starts with the same metadata header. Removing the header drops keyword search from 100% to 76% of dev questions with the right aid in the top five: that measurement is why we kept it.

## Slide 7: Step 2 · Hand check: 40 samples read, cut confirmed
The brief's tip: open 20 random documents and 20 random pieces before trusting a cutting strategy
What we read
20 random aids
20 random pieces
Fixed random seed (42): anyone can redraw the same sample
Record: docs/reviews/chunking-review.md
What we found
Answers (rates, ceilings, who qualifies) sit in short sections kept whole
Split sections lost their line breaks
Many aids list exclusions: “heat pumps not eligible”
Some aids give no amount at all
What we did
Fixed: line breaks kept
Rule for the answering model: respect “not eligible”
Rule: say “amount not stated”, never invent one
Added 3 test questions for these traps (q033–q035)
Verdict: CONFIRMED · 1 aid = 1 piece, long aids split by section, header on every piece
Notes: We read 40 random samples by hand. The cutting works: the facts people ask about sit in short sections that stay whole. Two traps go to the answering model's rules: exclusions and missing amounts. Each has a test question in the held-out set.

## Slide 8: Step 2 · Keyword search: great on names, not synonyms
BM25 scores a piece by the question words it contains, rare words counting more
1
Lowercase, drop accents
“Écologique” = “ecologique”
2
Remove common words
le, de, pour, les…
3
Keep word roots
“subventions” → “subvent”
17 / 17
dev questions: right aid in top 5
14 / 16
held-out questions: right aid in top 5
Why it missed q028 (ranked 11th)
The question says
“J'ai une entreprise de livraison en vélo cargo à Saintes…”
The aid says
“…logistique du dernier kilomètre… cyclo-entrepreneurs… cycles”
Same meaning, different words. Real users never use the official wording, so we need search by meaning too (step 4).
Dev = 20 questions used for tuning (17 have an answer in our data). Held-out = 20 questions only used for final scores (16 answerable).
Notes: Keyword search finds aids that share the question's words. It is perfect on dev, where questions often name the aid, but misses two held-out questions written in everyday words. The cargo-bike example shows why: no shared words with the aid's official text.

## Slide 9: Step 3 · Exam machine: 40 questions, auto-scored
Brief: “no component is working until it is scored on a held-out golden set with cost and latency tracked”
Chart: The 40 test questions by type
| Facts (amount, rate) | Eligibility | Location | Deadline | Exclusion | No amount given | Not in our data | Prompt injection
Dev (tune on these) | 6 | 4 | 3 | 3 | 0 | 0 | 2 | 2
Held-out (final score only) | 4 | 3 | 3 | 2 | 2 | 1 | 3 | 2
Two sets, never mixed
Dev (q001–q020): we tune on these
Held-out (q021–q040): final scores only
No aid appears in both: a test enforces it
run_eval.py logs, per question
Answer + cited sources · retrieved aid IDs
Tokens in / out (→ cost)
Latency, tool calls, stop reason
uv run python eval/run_eval.py --questions eval/golden.jsonl --out eval/
Runner by Saouss (PR #6); dev/held-out reporting added in PR #7. Answer-quality scores fill in once the answering model exists.
Notes: The exam machine is the brief's exact command. It asks all 40 questions and records the fields the brief requires. We tune only on the 20 dev questions and keep the 20 held-out ones for honest final scores. The held-out set adds the traps found in the hand check: exclusions and missing amounts.

## Slide 10: Step 4 · Meaning search: 3 models tested, bge-m3 wins
An embedding model turns text into a “meaning fingerprint”; close fingerprints = same meaning, even with different words
Chart: Right aid ranked 1st (meaning search alone)
| Keyword (BM25) | e5-small | e5-base | bge-m3
Dev | 73.5 | 73.5 | 73.5 | 91.2
Held-out | 75 | 75 | 62.5 | 87.5
Model | Size | Time / question | RAM
e5-small | 0.5 GB | 39 ms | 1.6 GB
e5-base | 1.1 GB | 86 ms | 2.4 GB
bge-m3 | 2.3 GB | 219 ms | 2.6 GB
All three find the right aid in the top 5 for 16/16 held-out questions. They differ on rank 1.
Decision: bge-m3. Best at ranking the right aid first (+17 points dev, +13 held-out). 0.2 s per question is small next to the seconds the answering model will need. Chosen on dev; held-out confirms.
Source: eval/retrieval_dense.json, measured on this laptop (CPU only). Exact versions pinned in the README. Model files are not in git.
Notes: We tested three free multilingual models on this laptop. All three find the right aid somewhere in the top five; bge-m3 is the only one that clearly improves the first result. It is bigger and slower, but still fast enough. We chose on the dev questions and the held-out questions confirm it.

## Slide 11: Step 4 · Two findings from the bge-m3 test
1) Merging keyword + meaning lowered rank 1 (fixed in step 5, next slide). 2) A lead for “I don't know”.
Chart: Right aid ranked 1st
| Keyword only | bge-m3 only | Hybrid (merged)
Dev | 73.5 | 91.2 | 85.3
Held-out | 75 | 87.5 | 75
Keyword search pushes wrong aids up when both count equally. Step 5 tests rerankers and a cheaper fix.
A lead for saying “I don't know”
bge-m3's best match score, per question type
≥ 0.617
questions we can answer (lowest seen)
≤ 0.613
questions with no answer in our data (highest seen)
Caution: based on only 3 “not in our data” questions, with a 0.004 gap. A promising threshold, not a rule yet. The e5 models mix the two groups up completely.
Source: eval/retrieval_dense.json. Top-5 recall is unaffected: hybrid finds the right aid in the top 5 for 17/17 dev and 15/16 held-out questions.
Notes: Two findings from the bge-m3 run. First, merging keyword and meaning search lowers how often the right aid is ranked first, because keyword search promotes wrong aids; the reranker is meant to fix that. Second, bge-m3's confidence separates answerable questions from ones our data cannot answer, which could help the assistant abstain, but only three such questions back this up.

## Slide 12: Step 5 · Reranking tested: a free setting wins
A reranker re-reads question + candidate side by side. We measured 2 rerankers and 1 free setting that needs no model
Chart: Right aid ranked 1st
| Hybrid, equal weights | + mMiniLM reranker | + bge-reranker | Hybrid, meaning ×3
Dev | 85.3 | 85.3 | 91.2 | 91.2
Held-out | 75 | 50 | 75 | 87.5
Option | Extra time / question
+ mMiniLM reranker (0.5 GB) | +2.6 s
+ bge-reranker (2.3 GB) | +19.4 s
Meaning ×3 (a setting) | 0 s
Decision: default = hybrid with meaning ×3. bge-reranker stays as an on/off option: built and measured, off on a laptop CPU. Picked on dev with a rule fixed in advance; held-out only checked after.
This is the brief's “cost/latency trade-off”: +6 points on dev, +0 on held-out, for +19 s per question.
Source: eval/retrieval_rerank.json, eval/retrieval_fusion.json. Rerankers re-sort the top 10 pieces. No model was trained: all are ready-made and only measured.
Notes: We tested two cross-encoder rerankers. The small one made rank 1 worse; the strong one helped one dev question, nothing on held-out, and costs 19 seconds per question on this CPU. A free setting does better: in the merge, meaning search counts three times more than keyword search. Held-out rank 1 goes from 75 to 88 percent. The strong reranker stays in the code as an option.

## Slide 13: Decision log: what we chose, and the evidence
Every row can be defended in the Q&A with a number or a rule from the brief
Question | Choice | Why / evidence | Status
How to cut the aids? | 1 aid = 1 piece; long aids split by section | Fits 300–800 tokens; 40 samples read by hand | Done
Header on each piece? | Yes: name, type, region, funder, deadline | Top-5 recall 77% → 100% on dev | Done
Keyword engine | BM25 with French word roots | Required by the brief; strong on names and codes | Done
How to test fairly? | 40 questions: 20 dev + 20 held-out | Brief requires a held-out set; no shared aid | Done
Meaning model | bge-m3 | Rank-1: 91% dev / 88% held-out vs ≤ 75% for others | Done
How to merge both lists? | Rank fusion, meaning counts ×3 | Rank-1 held-out 75% → 88%, at zero cost; picked on dev | Done
Model files | Pinned versions, kept out of git | Reproducible; repo stays small | Done
Reranker | bge-reranker as an option, off by default | +0 held-out for +19 s per question on CPU; mMiniLM made it worse | Done
Earlier decisions (use case, 504-aid subset, git rules) are on slides 2–3.
Notes: This is the list to rehearse for the Q&A: each choice has either a measurement or a rule from the brief behind it.

## Slide 14: How we work: 8 pull requests, 35 automated checks
Every change goes through a pull request (PR): a proposal that a teammate reviews before it joins main
Merged
Open
#1
Data source & licence
#2
Dashboard & slides
#3
Exploration notebook
#4
Pieces + keyword search
#5
20 held-out questions
#6
Exam machine (run_eval)
#7
Dev / held-out reporting
#8
Meaning search + hybrid
Review before merging
#2 and #4 were merged with no approval
Proposal: GitHub rule “1 approval required” (Paulin, 2 min)
Re-run checks after merges
#5 and #6 were fine alone but clashed together: 1 check failed on main
Fixed by #7; now 35 checks pass on the PR #8 branch
Keep the repo tidy
5 finished branches deleted
Tick “Automatically delete head branches” in Settings
Open branches today: main, feat/dense-hybrid (PR #8), README_update (Léopold, no PR yet).
Notes: Eight pull requests so far, seven merged. Three lessons: always get one approval before merging; run the checks again after each merge, because two good PRs can clash; and delete branches once merged.

## Slide 15: Next 5 days: who does what (to fill in today)
Each step is “done” only when the exam machine scores it on the held-out questions
Day | Goal | Done when | Owner
Fri 16 | Review and merge PR #8 (meaning search + ranking) | 35 checks pass on main | ?
Sat 17 | Pick the answering model (Ollama, 2–3 small ones); answers with sources as checked JSON | run_eval logs answer, citations, tokens; “I don't know” works | ?
Sun 18 | Agent tools (filter by region, date, aid type; fetch one aid); injection defence; cost tracking | Tool calls logged; q039–q040 pass | ?
Mon 19 | Final scores on held-out; error analysis; residual risks; bonus UI | Results table + 5 explained failures | ?
Tue 20 | README with exact models; record backup demo; tag v1.0 before 23:59 | Fresh clone runs the brief's command | ?
Wed 21 | Defence: 10 min pitch + 5 min Q&A, everyone speaks | Each person owns 2–3 slides | ?
Bonuses in reach: simple UI (answer + sources + agent steps), date filters, local vs API model if the school provides keys.
Notes: Fill the owner column together. The critical path is reranker, then answering model, then agent tools, then final scores. Keep Tuesday for polish and the backup demo video only.