## Slide 1: Roadmap: 2 of 11 steps done, 6 days to code freeze
RAG assistant on French green & innovation business aids · status as of 14 Oct 2026
Done
Partly done
Blocked
Not started
13–14 Oct
0
Scoping
14 Oct
1
Data foundations
15 Oct
2
Feature engineering
15–16 Oct
3
Search + eval harness
16 Oct
4
Local model choice
16–17 Oct
5
Answer generation
17 Oct
6
Agent + tracking
18–19 Oct
7
Evaluation, 40 questions
19 Oct
8
Bonuses + UI
20 Oct
9
Code freeze v1.0
21 Oct
10
Defence
TODAY
in review
blocked by merge
Accomplished
Scoping: use case, 504 aids, git rules
Corpus, data card, 20 test questions, 17 passing checks
Feature engineering part 1: text cleaned; tags for region, deadline, company size
Next, in order
Saouss reviews PR #1, then we merge
Close Chrome, then benchmark small local models on this laptop
Finish chunking; build search and run_eval.py together
Bonuses (extra credit)
Do: deadline and date filters
Do: simple UI with answer, sources and agent steps
Maybe: local vs API model, only if the school gives keys
Skip: database server, too heavy for this laptop
Source: repo and GitHub audit, 14 Oct 2026. Dates are targets; owners per step are proposed, not yet agreed.
Notes: Steps 0-1 are done (Phase 1, merge pending review). Step 2 is half done: cleaning and metadata exist; placeholder expansion and chunking remain. Step 4 is blocked until PR #1 is merged and memory is freed. Build the eval harness with retrieval so every later change is scored.

## Slide 2: What we have built so far: a verified foundation
Steps 0–1 of the roadmap, plus the first half of feature engineering
504
aids selected from 2,442
20 / 40
test questions written
17 / 17
automated checks passing
1
error in the government data found and fixed
1
Chose the use case
A funding finder for SMEs with a green or innovation project; scope and git rules agreed
2
Selected 504 aids
2,442 → 504 with three checkable rules: enough text, no duplicates, green or innovation
3
Confirmed the source
data.gouv.fr “Aides entreprises”, Licence Ouverte; all 504 aids match today's official file
4
Enriched every aid
Region, deadline, company size, aid type and funder added; a region error in the source fixed
5
Wrote 20 test questions
Facts, eligibility, regions, deadlines, plus trick questions and hacking attempts
6
Built a safety net
17 automated checks, an identical rebuild with one command, and a full data card
Known limits: 47% of local aids have no region on file · 15 dead source links · test set half done · PR #1 awaiting Saouss's review
Notes: Phase 1 delivered the data foundation. The corpus is rule-based and reproducible: anyone can rebuild the identical 504-aid file from the raw data with one command. The source and licence are confirmed (data.gouv.fr, Licence Ouverte v1.0). We found and fixed a source-data error: three Picardie departments were linked to Occitanie. Nothing is answered by a model yet: search, model and agent are Phase 2.

## Slide 3: How the 9 files fit together: one record per aid
aides.csv points to lookup tables by ID; we join 5 of them into every aid
Joined
Partly joined
Not used
natures.csv · 12 rows
Aid type: grant, loan, tax relief… · 503 of 504 aids
projets.csv · 101 rows
Project themes, used for the green + innovation filter · 504 of 504
profils.csv · 17 rows
Eligible business profiles (industry, crafts, retail…) · 504 of 504
financeurs.csv · 1,427 rows
Funder names, and postcodes used to infer some regions · 504 of 504
territoires.csv · 39,348 rows
Area → region, fixed with an official region table · 228 of 432 local aids
contacts.csv · 7,925 rows
Contact IDs kept, details not joined yet (Phase 2 if needed) · 503 of 504
aides.csv
2,442 aids, filtered to 504
aids.jsonl
504 clean records, labels instead of IDs
Not used
domaines.csv domain names already written in aides.csv
niveaux.csv national / regional / EU level already in aides.csv
Joins are made on IDs (e.g. aides.natures → natures.id_typ). Counts are from data/processed/aids.jsonl, checked 14 Oct 2026. No external dataset was merged.
Notes: The raw dataset is relational: aides.csv stores IDs that point to lookup tables. The selection script resolves those IDs into readable labels and writes one self-contained record per aid. Territories needed a correction: the source links three Picardie departments to Occitanie, so regions come from an official department-to-region table. Contacts are kept as IDs only for now.